**Progress Report for Technical Description**

1. Introduction
   1. Purpose

This report provides the current status of my English 314 technical description on Canon EOS T6 Rebel.

* 1. Background

On February 10, 2020, I proposed a technical description of the mechanism of a digital camera, Canon EOS T6 Rebel. You accepted my proposal, and we agreed that my technical description document would include a piece of in-depth technical information on the mechanism of Canon EOS T6 Rebel’s components. This including camera’s hardware and its software to process the image. The proposal report would also fulfill the formal report requirement for ENGL 314, Technical Communication.

* 1. Scope

This status report will include my current assessment of the project as of Saturday, March 7, 2020. The statement of work includes the following tasks:

Task 1: Understanding the primary mechanism of a digital camera, specifically Canon EOS T6 Rebel to provide a more detailed context for this report. (2 hours)

Task 2: Research and document the function of aperture in Canon EOS T6 Rebel and provide the reason of its existence. (4 hours)

Task 3: Research and document how the shutter speed may affect the result of an image. (4 hours)

Task 4: Describe the different configuration settings of the camera to capture image in a different environment. (3 hours)

Task 5: Produce and deliver a document based on the assignment requirement. (5 hours)

1. Status
   1. Tasks Completed

Task 1: I successfully completed the review on February 20, 2020, without any obstacles.

Task 2: I successfully completed this task on March 2, 2020 but had a little trouble in putting down the information into the document.

* 1. Tasks Remaining

Task 3: I have not completed this task; However, I had completed all the research regarding that component and will complete the task by March 10, 2020.

Task 4: The task is not complete. I had plan out what to be included in this document and I expect it to be done by March 10, 2020.

Task 5: The initial drafts of the document is completed. The final draft will be finalized once task 3 and 4 were completed. I will work on this document with my groupmates to produce a deliverable document as scheduled on March 12, 2020.

1. Conclusion
   1. Assessment

I am happy with the project to date and assess my progress as excellent. Most of

my research regarding the mechanism of its component has been completed, and I am

making a decent pace on including detailed information into the documents. The

remaining tasks should be completed by March 10, 2020. I will have the remaining

time to produce the final deliverable document, and deliver it as

required by March 15, 2020.

* 1. Contact

For more information, please send me an email at [wxlim@iastate.edu](mailto:wxlim@iastate.edu), or call

(555) 555-5555.